## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
|  | This is an example. This is a new line • Point 1 • Point 2 • Point 3 |  |  | This is an example. This is a new line 1. List 1 2. List 2 3. List 3
E01a | authentication | As an administrator, I want to be able to authenticate and authorize users. | Very High | 1 | Users can create an account with a unique username and password. User authentication is secure and follows industry standards. User roles and permissions can be assigned by administrators. | 3 story points | 3.1 | 3.6
E01b | manage | As a user, I want to be able to manage my profile | High | 1 | Users can view and update their personal information. Users can upload and manage their profile picture. Users can change their password. | 5 story points | 3.2 | 3.7
E01c | permission | As an administrator, I want to be able to manage user roles and permissions. | medium | 1 | Administrators can create, update, and delete user roles. Administrators can assign and revoke permissions for each role. Role-based access control is enforced throughout the system. | 4 story points | 3.2 | 3.8
E02a | contract | As a user, I want to be able to create a new contract. | medium | 2 | Users can select a contract template or create a new one from scratch. Users can enter contract details such as parties involved, effective date, and duration. Users can add and edit contract clauses and terms. | 2 story points | 3.9 | 3.11
E02b | review | As a user, I want to be able to review and revise contracts | low | 2 | Users can track and view the version history of a contract. Users can compare different versions of a contract and see the changes. Users can add comments and annotations to specific sections of a contract | 3 story points | 3.1 | 3.18
E02c | sign | As a user, I want to be able to electronically sign contracts | medium | 2 | Users can digitally sign contracts using a secure electronic signature method. Signed contracts are legally binding and tamper-proof. Users can track the signing status of a contract. | 5 story points | 3.1 | 3.18
E03a | receive reminders | As a user, I want to receive reminders and notifications for contract deadlines. | medium | 3 | Users receive automated notifications for contract expiration dates and renewal deadlines. Users can configure notification preferences (e.g., email, push notifications). | 3 story points | 3.19 | 3.31
E03b | track the status | As a user, I want to track the status and progress of contract execution. | high | 3 | Users can view the current status (e.g., pending, in progress, completed) of each contract. Users can see a timeline of activities and milestones related to a contract's execution. Users can generate reports on contract execution metrics. | 4 story points | 3.19 | 3.31
E03c | store and manage | As a user, I want to store and manage supporting documents related to a contract. | high | 3 | Users can upload and attach files (e.g., PDFs, Word documents) to a contract. Users can categorize and search for documents based on contract metadata. Users can download and share contract-related documents securely. | 2 story points | 3.21 | 3.31